## GANTTCHART
ONLINE LIBRARY MANAGEMENT SYSTEM
CRITICAL PATH
| Project Start Date | 2021-01-11 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Rakim Baliwena | [6 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01
 | time axis 2021-01-11 to 2021-03-07
TASK No | TASK | LEAD | DEPENDENT ON | START | END | DAYS | % DONE | WORK DAYS | time axis 2021-01-11 to 2021-03-07
1 | Write a project proposal |  |  | 11/01/21 | 11/01/21 | 1 | 100% | 1
2 | Specify project objectives |  |  | 2021-01-12 | 2021-01-12 | 1 | 0% | 2
3 | Develop a work plan |  | 2 | 2021-01-13 | 2021-01-14 | 2 | 0% | 2
4 | Gather system's functional requirements |  | 2 | 2021-01-15 | 2021-01-15 | 1 | 0% | 1
5 | Gather system's non-functional requirements |  | 2 | 2021-01-15 | 2021-01-15 | 1 | 0% | 1
6 | Create a Use case diagram |  | 4 | 2021-01-16 | 2021-01-17 | 2 | 0% | 2
7 | Create a Class diagram |  | 4 | 2021-01-18 | 2021-01-19 | 2 | 0% | 1
8 | Create an Entity Relation Diagram |  | 4 | 2021-01-20 | 2021-01-21 | 2 | 0% | 2
9 | Create a business process flow diagram |  | 4 | 2021-01-22 | 2021-01-23 | 2 | 0% | 1
10 | Determine the tasks to be done throughout the project |  | 1,2,3,4,5 | 2021-01-24 | 2021-01-24 | 1 | 0% | 0
11 | Identify the dependencies of the tasks |  |  | 2021-01-24 | 2021-01-24 | 1 | 0% | 0
12 | Identify the risks associated with the project |  |  | 2021-01-25 | 2021-01-25 | 1 | 0% | 1
13 | Determine strategies to overcome the risks associated with the project. |  | 12 | 2021-01-25 | 2021-01-25 | 1 | 0% | 1
14 | Determine the critical path of the system |  | 2,3 | 2021-01-26 | 2021-01-28 | 3 | 0% | 3
15 | Identify tools and technologies used to implement the system |  | 2,4,5 | 2021-01-29 | 2021-01-29 | 1 | 0% | 1
16 | Prepare for the implementation phase |  | 4,5 | 2021-01-30 | 2021-01-31 | 2 | 0% | 0
17 | Create the database for the system |  | 4 | 2021-02-01 | 2021-02-04 | 4 | 0% | 4
18 | Create a default administrator in the database. |  |  | 2021-02-05 | 2021-02-05 | 1 | 0% | 1
19 | Create a login page |  |  | 2021-02-05 | 2021-02-05 | 1 | 0% | 1
20 | Create an administrator profile page. |  |  | 2021-02-06 | 2021-02-07 | 2 | 0% | 0
21 | Add a feature to enable the administrator to login to the system |  | 18,19 | 2021-02-08 | 2021-02-08 | 1 | 0% | 1
22 | Add a feature to enable authentication for the administrator login |  | 21 | 2021-02-09 | 2021-02-09 | 1 | 0% | 1
23 | Create a librarian registration page. |  |  | 2021-02-10 | 2021-02-10 | 1 | 0% | 1
24 | Create a librarian home page |  | 23 | 2021-02-11 | 2021-02-11 | 1 | 0% | 1
25 | Add a feature to enable administrator to register librarians into the system |  |  | 2021-02-12 | 2021-02-12 | 1 | 0% | 1
26 | Add a feature to enable librarians to login to the system. |  | 25,19 | 2021-02-13 | 2021-02-13 | 1 | 0% | 0
27 | Add a feature to enable authentication for the librarian login |  | 26 | 2021-02-14 | 2021-02-14 | 1 | 0% | 0
28 | Add a feature to enable librarians to add books to the catalog according to categories in the system |  |  | 2021-02-15 | 2021-02-15 | 1 | 0% | 1
29 | Add a feature to enable librarians to remove books from the catalog in the system |  |  | 2021-02-16 | 2021-02-16 | 1 | 0% | 1
30 | Create a search panel to search for books in the system |  |  | 2021-02-17 | 2021-02-17 | 1 | 0% | 1
31 | Create a page for a list view. |  |  | 2021-02-18 | 2021-02-18 | 1 | 0% | 1
32 | Add the search panel on the librarian's homepage |  | 30 | 2021-02-19 | 2021-02-19 | 1 | 0% | 1
33 | Add a feature to enable librarians to view all the books available in the system using the list view page |  | 28,31 | 2021-02-20 | 2021-02-20 | 1 | 0% | 0
34 | Add a feature to enable the librarians to view all unavailable books (which have been borrowed) |  | 31 | 2021-02-21 | 2021-02-21 | 1 | 0% | 0
35 | Create a page for the librarian for adding payment information for a member |  |  | 2021-02-22 | 2021-02-22 | 1 | 0% | 1
36 | Add a feature to enable librarian to add payment status of an applicant into the system. |  |  | 2021-02-23 | 2021-02-23 | 1 | 0% | 1
37 | Create a member registration page |  |  | 2021-02-24 | 2021-02-24 | 1 | 0% | 1
38 | Add a feature to enable librarian to register members to the system |  |  | 2021-02-25 | 2021-02-25 | 1 | 0% | 1
39 | Restrict the system from registering a member that has not paid registration fees |  |  | 2021-02-26 | 2021-02-26 | 1 | 0% | 1
40 | Create a page for allocating a book to a member |  |  | 2021-02-27 | 2021-02-27 | 1 | 0% | 0
41 | Add a feature to enable librarian to checkout an available book to a member. |  |  | 2021-02-28 | 2021-02-28 | 1 | 0% | 0
42 | Add a feature to change the status of the book in the system once it has been checked-out |  | 41 | 2021-03-01 | 2021-03-01 | 1 | 0% | 1
43 | Add a feature to enable librarian to check-in a book returned by a member. |  |  | 2021-03-02 | 2021-03-02 | 1 | 0% | 1
44 | Add a feature to update the status of the book after it has been returned by a member. |  | 43 | 2021-03-03 | 2021-03-03 | 1 | 0% | 1
45 | Create an online registration page for the members. |  |  | 2021-03-04 | 2021-03-04 | 1 | 0% | 1
46 | Create a homepage for the member with profile information. |  |  | 2021-03-05 | 2021-03-05 | 1 | 0% | 1
47 | Add a feature to view books from the library on the member's home page. |  |  | 2021-03-06 | 2021-03-06 | 1 | 0% | 0
48 | Add a feature to enable the member to register online if he/she has made payment. |  |  | 2021-03-07 | 2021-03-07 | 1 | 0% | 0
49 | Add a feature to enable the member to login to the system |  | 19 | 2021-03-08 | 2021-03-08 | 1 | 0% | 1
50 | Add a feature to enable authentication of the member during login. |  |  | 2021-03-09 | 2021-03-09 | 1 | 0% | 1
51 | Add a search panel on the member's homepage. |  |  | 2021-03-10 | 2021-03-10 | 1 | 0% | 1
52 | Add a feature to enable the member to use a search panel to browse for books. |  |  | 2021-03-11 | 2021-03-11 | 1 | 0% | 1
53 | Add a button on the view page to allow the member to borrow a book when clicked. |  |  | 2021-03-12 | 2021-03-12 | 1 | 0% | 1
54 | Add a feature to enable the member to borrow a book online if it is available. |  |  | 2021-03-13 | 2021-03-13 | 1 | 0% | 0
55 | Add a feature to Enable a member to reserve a book that has been borrowed by someone else. |  |  | 2021-03-14 | 2021-03-14 | 1 | 0% | 0
56 | Add a feature to update the status of a reserved book to the librarian. |  | 55 | 2021-03-15 | 2021-03-15 | 1 | 0% | 1
57 | Create a notification panel on the member's page. |  |  | 2021-03-16 | 2021-03-16 | 1 | 0% | 1
58 | Add a feature to notify the member when a reserved book has been returned and is available. |  | 57 | 2021-03-17 | 2021-03-17 | 1 | 0% | 1
59 | Add a feature to automatically cancel a reservation when it has not been attended to after 24 hours of the book being available again. |  | 53 | 2021-03-18 | 2021-03-18 | 1 | 0% | 1
60 | Add a feature to allow a member to keep a book until 2 weeks from date of borrowing otherwise, start adding to the fine fee 200Tshs per each extended day that a member has not returned the book |  | 54 | 2021-03-19 | 2021-03-19 | 1 | 0% | 1
61 | Add a feature to restrict a member from borrowing more than 3 books |  | 54 | 2021-03-20 | 2021-03-20 | 1 | 0% | 0
62 | Add a feature to cancel membership of a person 6 months after the date of registration. |  |  | 2021-03-21 | 2021-03-21 | 1 | 0% | 0
63 | Add a feature to notify a member 1 week before the membership expiry date |  | 57 | 2021-03-22 | 2021-03-22 | 1 | 0% | 1
64 | Create a page to allow the librarian to view all members of the system using the list view page. |  | 31 | 2021-03-23 | 2021-03-23 | 1 | 0% | 1
65 | Create a page to allow a librarian to view all those whose membership has expired using the list view page |  | 31,62 | 2021-03-24 | 2021-03-24 | 1 | 0% | 1
66 | Add a feature to allow the librarian to renew the membership of an applicant if he/she has paid on the registration page |  |  | 2021-03-25 | 2021-03-25 | 1 | 0% | 1
67 | Create a page to allow the member to renew their membership online if he/she has paid |  |  | 2021-03-26 | 2021-03-26 | 1 | 0% | 1
68 | Create a page where administrator can view all librarians using the list view page |  | 31 | 2021-03-27 | 2021-03-27 | 1 | 0% | 0
69 | Test the system |  |  | 2021-03-28 | 2021-04-02 | 6 | 0% | 5
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.